Quick Summary of Requirements – BCPS Solicitation NGO-408-26

🔹 Requested Services

BCPS is seeking qualified vendors to deliver:

- Professional Workshops – Structured training sessions for educators and staff.

- Speaking Engagements – Inspirational or educational talks aligned with BCPS values.

- Coaching & Team Development – Programs that build collaboration, resilience, and leadership.

- Board Hearing Examiner Services – Legal or mediation services for internal hearings.

🔹 Proposal Requirements

Vendors must:

- Demonstrate relevant experience in each selected service category.

- Describe program offerings with clear structure and outcomes.

- Align with BCPS’s mission to Engage, Empower, Excel.

- Include certified small business participation (15% MBE/SBE goal encouraged).

- Submit a complete proposal with capability statements, pricing, and compliance documentation.

🔹 Evaluation Criteria

Proposals will be scored based on:

- Experience and qualifications

- Program structure and clarity

- Alignment with BCPS goals

- Diversity and inclusion participation

- Overall proposal quality

📅 Bid Preparation Schedule

Week 1 (Nov 11–15)

- Nov 11 (Today): Attend pre-bid meeting (already scheduled). Take notes on clarifications.

- Nov 12–13: Review full solicitation documents carefully. Highlight mandatory forms, compliance requirements, and evaluation criteria.

- Nov 14: Draft outline of proposal sections:

  - Cover letter / executive summary

  - Capability statement (tailored to BCPS)

  - Technical approach (workshops, speaking engagements, hearing examiner services)

  - MBE/SBE participation plan

  - Past performance / qualifications

- Nov 15: Identify potential MBE/SBE partners. Reach out to confirm interest and obtain certifications/commitments.

Week 2 (Nov 16–22)

- Nov 16–17: Write full draft of proposal narrative. Incorporate your VSBE certification and values-based mediation differentiators.

- Nov 18: Insert partner details into MBE/SBE participation section. Draft the Utilization Affidavit.

- Nov 19: Internal review—check alignment with BCPS motto (Engage. Empower. Excel.) and compliance requirements.

- Nov 20: Revise and polish proposal. Ensure formatting matches submission guidelines.

- Nov 21–22: Prepare final attachments (affidavits, certifications, resumes, references). Assemble into one PDF.

Final Days (Nov 23–25)

- Nov 23: Conduct a compliance checklist:

  - All required forms included

  - Proposal sections complete

  - File format correct (PDF)

  - Minority participation plan documented

- Nov 24: Upload test draft to submission portal (if allowed) or rehearse submission process.

- Nov 25 (Deadline Day): Submit final proposal no later than 11:00 AM to avoid last-minute issues. Keep confirmation email/receipt.

🎯 Key Reminders

- Submit early—don’t wait until 2:00 PM.

- Follow up with partners quickly to lock in MBE/SBE commitments.

- Keep a version control system (e.g., Proposal Draft v1, v2) so edits don’t get lost.

- Document everything—BCPS may ask for proof of certifications or commitments late

Alignment Summary

Professional Mediations LLC delivers Baltimore City Public Schools a rare combination of combat-tested leadership, legal authority, and values-based mediation. As an active Maryland attorney since 2020, former VA General Counsel, and nationally certified mediator, I bring both procedural rigor and human-centered fairness to every engagement. My career has been shaped by service: leading over 200 combat patrols in Iraq as a 2LT, serving on President George W. Bush’s inaugural security detail, and directing a UN-supervised chemical weapons recovery mission in the Solomon Islands.

Equally important, I have worked at the community level—providing free legal support to veterans under Judge Jews in Cambridge, MD, partnering with the Office of Parole and Probation and United Way to support the Anne Arundel Veterans Treatment Court, and organizing pro-bono legal initiatives with Northrop Grumman’s General Counsel. These experiences demonstrate my ability to engage diverse partners, empower underserved communities, and excel in delivering principled leadership.

This proposal aligns directly with BCPS’s mission to Engage, Empower, and Excel by offering workshops, speaking engagements, coaching, and examiner services that are structured, professional, and grounded in lived leadership experience across federal, state, local, and international contexts.

📌 Capability Statements

Workshops & Training

- Designed national VA training modules introducing Veterans Treatment Courts.

- Delivered a three-day administrative investigations program with interviewing exercises and mock presentations.

- Re-engineered VA compliance training to replace legal jargon with interaction-based modules focused on user experience.

- Facilitated round-table veterans’ rights training at McVets, adapting instruction to participant needs.

- Partnered with Anne Arundel Veterans Treatment Court, Parole & Probation, and United Way to provide free legal support and training.

Speaking Engagements

- Keynote speaker for Howard County Bar Association on veterans, overcoming adversity, and leadership.

- Guest speaker for VA Regional Counseling Services Leadership Retreat.

- Combat veteran story (200+ patrols in Iraq) used to inspire resilience and principled leadership.

- Selected for President George W. Bush’s inaugural security detail, offering unique insights into resilience and support systems.

Coaching & Team Development

- Led 200+ combat patrols in Iraq as a 2LT, building trust, cohesion, and mission focus under pressure.

- Organized pro-bono legal day with Northrop Grumman General Counsel, convening diverse partners to serve homeless veterans.

- Directed UN-supervised chemical weapons recovery mission in the Solomon Islands, coordinating multinational teams in high-risk environments.

- Facilitated dialogue-driven coaching for homeless veterans at McVets.

Board Hearing Examiner Services

- Active Maryland attorney since 2020.

- Law clerk for Hon. Kevin J. Mahoney (Harford County).

- Provided free legal support to veterans under Judge Jews (Cambridge, MD).

- Former VA General Counsel, ensuring procedural fairness and impartiality in employment disputes.

- Founder of Professional Mediations LLC, delivering values-based conflict resolution that preserves relationships.

- Military and international leadership roles reinforce credibility in discipline, impartiality, and principled decision-making.

Commitment to Diversity & Inclusion

- Certified Veteran-Owned Small Business Enterprise (VSBE) under Maryland law.

- Proven record of engaging diverse partners—from corporate counsel to community organizations—to expand access and impact.